## Summary
Field | Value
Benchmark scope | 3 methods x 3 protocols for the longitudinal benchmark
Methods | Zero-shot ¦ Autoformalization ¦ Official
Protocols | Single-step ¦ Rolling, no history ¦ Rolling, with history
Current implemented protocol in code | Rolling, no history
Why | history is reinitialized inside each checkpoint loop in src/sepsis_mvp/environment.py
Best completed benchmark slice | Single-task sepsis, rolling without history, official vs autoformalized
Zero-shot recommendation | Scale back zero-shot from full sepsis to infection-only with a simplified YAML
Multitask status | Useful but incomplete: official 94/96 trajectories, autoformalized 59/96 trajectories
AKI status | Current AKI non-monotonic artifacts are smoke runs only, not final benchmark rows
New benchmark to build | Single sepsis: within 24h of ICU admission, when is SOFA onset?
Reference note | See docs/benchmark_experiment_audit.md for the reasoning and run queue

## Experiment Matrix
Benchmark Slice | Method | Protocol | Status | Metrics Available | Evidence / Artifact | Next Action
Full sepsis | Official | Rolling, no history | COMPLETE | step acc 0.8003; macro F1 0.6152 | result/single_sepsis_Qwen3-30B-A3B-Instruct-2507/qwen_eval.json | Use as current reference baseline
Full sepsis | Autoformalization | Rolling, no history | COMPLETE | step acc 0.6589; macro F1 0.5463 | result/auto_sepsis_Qwen3-30B-A3B-Instruct-2507/auto_qwen_sepsis_qwen_eval.json | Use as current comparison baseline
Full sepsis | Zero-shot | Rolling, no history | BLOCKED | No eval; partial debug trace only | result/zeroshot_sepsis_Qwen3-30B-A3B-Instruct-2507/zeroshot_sepsis_events.jsonl | Deprioritize full-sepsis zero-shot; move to infection-only
Full sepsis | Official | Single-step | MISSING |  |  | Implement protocol
Full sepsis | Autoformalization | Single-step | MISSING |  |  | Implement protocol
Full sepsis | Zero-shot | Single-step | MISSING |  |  | Implement protocol after infection-only zero-shot
Full sepsis | Official | Rolling, with history | MISSING |  |  | Carry forward concise step summaries across checkpoints
Full sepsis | Autoformalization | Rolling, with history | MISSING |  |  | Carry forward concise step summaries across checkpoints
Full sepsis | Zero-shot | Rolling, with history | MISSING |  |  | Only consider after infection-only zero-shot is stable
Infection-only | Official | Rolling, no history | PLANNED |  |  | Create infection-only dataset / simplified guidance
Infection-only | Autoformalization | Rolling, no history | PLANNED |  |  | Create infection-only dataset / simplified guidance
Infection-only | Zero-shot | Rolling, no history | PLANNED |  |  | Main zero-shot benchmark slice to run next
AKI non-monotonic | Official | Rolling, no history | SMOKE ONLY | heuristic, n=3, step acc 1.0000 | data/aki_non_monotonic_eval.json | Rerun with Qwen on full cohort
AKI non-monotonic | Autoformalization | Rolling, no history | SMOKE ONLY | heuristic, n=1, step acc 0.2857 | data/aki_non_monotonic_auto_eval.json | Rerun with Qwen on full cohort
Multitask | Official | Rolling, no history | PARTIAL | joint step acc 0.5775 on 94/96 | result/official_multi_Qwen3-30B-A3B-Instruct-2507/qwen_multitask_eval.json | Finish missing 2 trajectories or rerun matched cohort
Multitask | Autoformalization | Rolling, no history | PARTIAL | joint step acc 0.3269 on 59/96 | result/auto_multi_Qwen3-30B-A3B-Instruct-2507/auto_qwen_multitask_eval.json | Rerun to full matched 96-stay cohort
Single sepsis SOFA-onset | Official | Protocol comparison | PLANNED |  |  | Build dedicated within-24h onset benchmark
Single sepsis SOFA-onset | Autoformalization | Protocol comparison | PLANNED |  |  | Build dedicated within-24h onset benchmark

## Current Results
Slice | Method | Cohort / Coverage | Step Accuracy | Macro F1 | Other Key Metric | Quality Note | Primary Artifact
Single-task sepsis | Official | 98 trajectories | 0.8003 | 0.6152 | infection MAE 3.1667h; alert MAE 2.9167h | Best completed single-task baseline | result/single_sepsis_Qwen3-30B-A3B-Instruct-2507/qwen_eval.json
Single-task sepsis | Autoformalization | 98 trajectories | 0.6589 | 0.5463 | infection missed rate 0.5102 | Completed but weaker than official | result/auto_sepsis_Qwen3-30B-A3B-Instruct-2507/auto_qwen_sepsis_qwen_eval.json
Multitask | Official | 94 / 96 trajectories | 0.5775 |  | Sepsis F1 0.5848; AKI F1 0.7973; RR F1 0.9519 | Directionally useful, not final matched cohort | result/official_multi_Qwen3-30B-A3B-Instruct-2507/qwen_multitask_eval.json
Multitask | Autoformalization | 59 / 96 trajectories | 0.3269 |  | Sepsis F1 0.5349; AKI F1 0.4711; RR F1 0.8400 | Incomplete cohort; do not treat as final table | result/auto_multi_Qwen3-30B-A3B-Instruct-2507/auto_qwen_multitask_eval.json
AKI non-monotonic smoke | Official | heuristic sample, n=3 | 1 | 1 | exact path match 1.0 | Smoke only | data/aki_non_monotonic_eval.json
AKI non-monotonic smoke | Autoformalization | heuristic sample, n=1 | 0.2857 | 0.375 | exact path match 0.0 | Smoke only | data/aki_non_monotonic_auto_eval.json
Zero-shot raw sepsis | Zero-shot | partial debug trace only |  |  | 30 events; no rollout/eval json | Not benchmarkable yet | result/zeroshot_sepsis_Qwen3-30B-A3B-Instruct-2507/zeroshot_sepsis_events.jsonl

## Open Items
Priority | Open Item | Why It Matters | Concrete Deliverable
P0 | Build infection-only benchmark slice | Needed to make zero-shot comparable without forcing full SOFA logic | Dataset + simplified YAML + 3 method runs under rolling/no-history
P0 | Finish multitask matched cohort | Current official vs auto comparison is coverage-mismatched | Full 96/96 official and auto runs or a clean matched rerun
P1 | Implement rolling-with-history protocol | Current code resets history every checkpoint | Carry forward concise sepsis summaries: step_index, sofa_score, infection, evidence
P1 | Implement single-step protocol | Needed for the 3-protocol benchmark grid | Runner mode that evaluates one checkpoint without prior checkpoint context
P1 | Build single sepsis SOFA-onset benchmark | This is the benchmark question you explicitly want to answer | Dedicated within-24h dataset and evaluation target
P2 | Run real AKI non-monotonic Qwen benchmarks | Current AKI evidence is only from smoke checks | Official and autoformalized full-cohort runs